## Slide 1: ATAR
Ciorbă Rareş (PM)

## Slide 2: Time plan
Lab number | Tasks | Tasks done
Lab 2 | Understanding and analyzing the requirements | 2/2
Lab 3 | Structuring the project (Sprint 1) | 12/12
Lab 4 | Coding phase 1 (Sprint 2) | 17/21
Lab 5 | Coding phase 2 (Sprint 3) | 23/23
Lab 6 | Coding phase 3 (Sprint 4) | 16/16
Lab 7 | Missing features and final presentation (Sprint 5) | 4/4

## Slide 3: Lab 2 – Understanding and analyzing the requirements
We first started by analyzing the requirements and creating a list of questions based on the harder to grasp concepts of the requirement.
Once we got all of the answers we then gathered everything together and started building a file containing all of the details related to the application, as well as the structure of the data, and the functionalities in it. (task.md)
We also decided on the programming language of the project (Kotlin) and the technology for the storage of our database (PostgreSQL). We decided to have a hosted database so that all of us can access the same data.

## Slide 4: Lab 3 - Structuring the project (Sprint 1)
In this sprint we started getting familiar with Kotlin and started building up a bare version of the project.
We primarily focused on use case diagrams as well as class diagrams. We focused on class diagrams in order to get a slight lead in case we get behind.

## Slide 5: Lab 4 - Coding phase 1 (Sprint 2)
In this sprint we started by adding the entities into the application, and setting up the ORM (ktorm).
We then continued by focusing on the functionalities related to the first phase, such as: account management, conference management, and the initial part of the proposal submission.
We corrected our use case diagrams and also got started with the sequence diagrams.
The tasks were more tedious than what we had expected, and thus, we didn’t meet the deadline for all of the tasks. However about all of them were nearing completion. To accomodate for this, we moved the tasks that we couldn’t finish to the next sprint.

## Slide 6: Lab 5 - Coding phase 2 (Sprint 3)
In this sprint we caught up to the tasks that we couldn’t finish during the last sprint, and focused on the second phase: proposal bidding and reviewing.
As for the documentation, we finished all of the sequence diagrams, and we adopted the class diagrams that we had in order to do the code generation required.

## Slide 7: Lab 6 - Coding phase 3 (Sprint 4)
In this phase, we fixed the minor issues in our application, as well as patched the bugs. We also quality of life enhancements.
We then focused on the manual, as well as updated the class diagram to include the final classes and the missing fields.

## Slide 8: Lab 7 - Missing features and final presentation (Sprint 5)
In this final sprint, after the teacher’s evaluation, we focused on the missing features of our application, thus completing the actual application in its entirety.
We then moved to creating the presentation based on our experience.

## Slide 9: Task management
For task management we decided to use GitHub projects. We created an issue for each task, where we wrote the description of what that task should be, as well as a check list (for some of them) to keep better track of the progress for the bigger ones.
During the second sprint (when we just started with the application), we found it hard to visualize how the application should look, and we created mockups for the UI.
After each lab, we had a meeting where we discussed the future plans of the application and split the tasks into issues.

## Slide 10: Coding process
The tasks were self assigned, and we all worked on separate branches on our designated tasks in order to facilitate working in parallel.
Once the tasks were done, we created a pull request on GitHub, where we decided that each pull request must have a minimum of two reviewers before it can be merged into master.
In general, we were in a voice call when we worked on our tasks. This made it easier for us to focus on our tasks as well as easily discuss any questions we had.
We decided to be consistent and thus use the same coding style across the whole project.

## Slide 11: Evaluation
We consider that we all split the tasks evenly among us